## Sheet1
Task Title | Start Date | Finish Date | Duration | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV
System Analysis | 28/02/2019 | 2019-12-03 | 13d | bar: FEB to MAR
Studying Technology | 28/02/2019 | 28/09/2019 | 213d | bar: FEB to SEP
Requirement Gathering | 17/03/2019 | 2019-06-11 | 235d
Feasibility Study | 17/03/2019 | 2019-01-04 | 16d | bar: MAR to APR
Competitor Analysis | 22/03/2019 | 31/03/2019 | 10d | bar: MAR
Use Case Designing | 20/03/2019 | 31/03/2019 | 12d | bar: MAR
SRS Documentation | 25/06/2019 | 26/08/2019 | 62d | bar: JUN to AUG
System Design | 2019-03-08 | 27/08/2019 | 25d | bar: AUG
UI Design | 2019-03-08 | 2019-01-09 | 30d | bar: AUG to SEP
Back-End Design | 2019-03-08 | 2019-01-09 | 30d | bar: AUG to SEP
Documentation | 28/07/2019 | 14/11/2019 | 110d | bar: JUL to NOV
Implementation | 2019-03-08 | 2019-10-11 | 149d | bar: AUG to NOV
Testing | 16/8/2019 | 2019-10-11 | 86d | bar: AUG to NOV
Deployment | 24/11/2019 | 30/11/2019 | 7d | bar: NOV